## Confidential
Confidential: For Internal and Partner Use Only
Copyright © 2026 Broadcom. All Rights Reserved. The term “Broadcom” refers to Broadcom Inc. and/or its subsidiaries.

## Full Version
Block | Category | Assessment Area | Capability Rating | Customer Deliverables | Evaluation Criteria | Key Steps | Dependencies | SOW Deliverable | Variations | Reference Tech Docs
1 | Platform Foundation | Assess & Review Workshop | Strongly Agree | In Progress | • VCF 9 Deployment Roadmap is signed off by executive and technical leads • Reseller Workshop mapped VCF Management Domain benefits to IT goals | • Conduct VCF 9 Capability Workshop to map business goals to VCF full-stack features • Define technical success criteria and KPIs for the 60-month adoption journey | None | • Signed VCF 9 Deployment Roadmap • Documented Business Case & KPI Map | • Infra: Greenfield vs Brownfield strategy session • Sec: Industry-specific compliance alignment (eg, HIPAA/PCI) | VCF Planning and Preparation
2 |  | Site Readiness Validation | Mostly Agree |  | • All VCF 9 deplpoyment prerequisites validated with a signed "Site Readiness Report" • Hardware compatibility (HCL) verified for all physical hosts and NICs | • Validate physical network (ToR, MTU) and hardware compatibility against the VCF 9 HCL • Verify DNS, NTP, and IP allocation prerequisites for the Management Domain | • Assess & Review Workshop | • Signed Site Readiness Report • Validated Infrastructure BOM/HCL Audit | • Infra: VxRail vs vSAN ReadyNode prerequisites • Sec: Air-gapped vs Connected environment prep | VCF Site Readiness Checklist
3 |  | VCF Management Domain (SDDC, Ops, NSX Manager, vCenter and Automation) | Mostly Disagree |  | • VCF 9 Management Domain is active, providing a single interface across all domains • Cross-component orchestration validated via global configuration task execution | • Complete the VCF 9 installer workflow to deploy a healthy Management Domain (>7 appliances) • Activate the VCF Management Console and verify cross-component orchestration capabilities | • Assess & Review Workshop • Site Readiness Validation | • Functional VCF Management Console accessible via SSO • Management Domain Build & Health Report | • Infra: Standard vs Consolidated architecture deployment • HA vs non HA Management domains | VCF Installer and Domain Creation
4 |  | Identity Broker & Multi-Tenancy | Mostly Agree |  | • Identity Broker is active, federating VCF instances into a single SSO domain • At least one Tenant Organization is defined with isolated RBAC and resource quotas | • Deploy the VCF Identity Broker and federate with the corporate Identity Provider (IdP) • Define initial Tenant Organizations with isolated RBAC and resource quotas | • VCF Mgmt Domain | • IdP Federation Configuration Document • Functional Multi-Tenant SSO Environment | • Infra: Single-site SSO vs Global Federated SSO • Sec: SAML vs OIDC integration requirements | VCF Identity Broker Configuration
5 |  | Solution License Management | Mostly Agree |  | • All VCF 9 entitlements registered in the Business Services Portal • Licenses visible in VCF Operations, showing usage across the fleet | • Register VCF 9 entitlements are in the Business Services Portal • Activate centralized license monitoring and reporting within VCF Operations | • VCF Mgmt Domain | • License Entitlement & Allocation Map • Active Fleet-wide License Consumption Dashboard | • Infra: Connected vs Disconnected (Dark Site) licensing • Sec: Core-based vs Legacy licensing conversion | VCF Operations License Management
6 | Storage / Datastore | Assess & Review (vSAN) | Strongly Agree |  | • Tier-1 app IOPS, latency, and throughput requirements are documented • vSAN ESA migration strategy is approved for legacy storage workloads | • Audit existing storage workloads to define SPBM performance requirements • Document the vSAN ESA failure domain and cluster-level design strategy | • Assess & Review Workshop | • Documented Storage Design & Migration Plan • Performance Baseline & Capacity Forecast | • Infra: SAN-to-vSAN migration vs Greenfield deployment • Sec: Data-at-rest encryption compliance requirements | vSAN Design Guide
7 |  | vSAN ESA Implementation | Mostly Agree |  | • vSAN ESA is active on NVMe hardware with performance testing completed • SPBM policies are defined and applied to 80% of production workloads | • Configure vSAN ESA clusters and validate hardware performance against baselines • Define and validate the SPBM policy catalog against workload requirements | • Site Readiness Validation • Assess & Review (vSAN) | • Functional vSAN ESA Cluster • Validated SPBM Policy Catalog | • Sec: Handling of mixed ESA/OSA environments • Infra: < 5ms latency (Standard) vs High-latency Stretch | vSAN Stretch Cluster Guide
8 |  | NVMe Memory Tiering | Mostly Disagree |  | • Memory tiering is active on host clusters with cold pages offloading to NVMe • Performance monitoring confirms measurable VM density increase (target 30-40%) | • Enable Memory Tiering on supported host clusters and verify NVMe targets • Validate "Cold Page" offloading and monitor for consolidation gains | • VCF Mgmt Domain | • Active NVMe Memory Tiering Configuration • Performance Report documenting consolidation gains | • Infra: Host-specific CPU/Memory architecture constraints • Sec: Data persistence requirements for tiered memory | vSphere Memory Tiering
9 | Networking & Connectivity (Network Fabric) | Assess & Review (NSX) | Strongly Agree |  | • Network underlay (MTU 1600+, BGP readiness) is documented and validated • Edge Cluster sizing and North-South exit strategy are approved | • Perform physical network audit for MTU and Jumbo Frame support • Document Edge Node placement and routing requirements (VLAN vs Overlay) | • Assess & Review Workshop | • Signed NSX Architecture & Design Document • Validated Underlay Readiness Report | • Infra: Dedicated vs Collapsed Edge design • Sec: Overlapping IP space (NAT) requirements | NSX Design Guide
10 |  | NSX Overlay Networking | Mostly Agree |  | • NSX Overlay fabric is active with all Transport Nodes successfully communicating • HA Edge Cluster is deployed and providing stable N-S routing services | • Deploy NSX Transport Zones and Uplink Profiles across host clusters • Configure HA Edge Nodes and establish the centralized Edge Cluster | • Site Readiness Validation • Assess & Review (NSX) | • Functional NSX Overlay Fabric • Validated HA Edge Cluster Config | • Infra: Bare Metal vs Edge VM sizing • Sec: Encryption requirements for N-S traffic | NSX Edge Deployment
11 |  | VCF VPC | Mostly Disagree |  | • VCF Transit Gateway is active and managing VPC-to-VPC routing • Non-admin users can successfully self-provision VPCs and verify connectivity | • Deploy the VCF Transit Gateway within the VCF Management Console • Configure VPC routing policies and validate developer-level access | • VCF Mgmt Domain • NSX Overlay Networking | • Functional VCF Transit Gateway • Validated VPC Self-Service Environment | • Infra: Isolated VPCs vs Shared Transit services • Sec: Inter-site Transit Gateway extension | VCF Networking & VPC
12 |  | NSX Edge Connectivity | Mostly Disagree |  | • Dynamic BGP peering is established between Tier-0 and physical ToR switches • Route redistribution and prefix lists are actively policing traffic flow | • Establish BGP peering and configure route redistribution policies • Validate North-South traffic path and ECMP performance | • NSX Overlay Networking | • Validated BGP Peering & Routing Report • Operational N-S Traffic Path | • Infra: Dynamic BGP vs Static routing • Sec: VRF-Lite vs Global routing table peering | NSX Routing & BGP
14 | Operational Observability | Assess & Review (VCF Operations) | Strongly Agree |  | • Monitoring thresholds and alerting notification paths are defined for all SDDC layers • Infrastructure metadata (Tags) is mapped to logical business applications | • Audit operational requirements for alerting and ITSM integration • Document the global tagging and metadata schema for fleet-wide visibility | • Assess & Review Workshop | • Signed Operations Design & Alerting Matrix • Documented ITSM Integration Plan | • Infra: Integrated VCF Ops vs 3rd-party (Splunk) • Sec: Data retention for performance metrics | VCF Operations Guide
15 |  | Dashboards & Logs | Mostly Agree |  | • Unified dashboards provide real-time visibility from hardware to application layers • Centralized log collection is active with real-time security alerting for system failures | • Activate full-stack dashboards and configure centralized log forwarding (VCF Operations for Logs) • Create persona-based views and configure critical log-based alerts | • VCF Mgmt Domain • Assess & Review (VCF Ops) | • Functional Persona-Based Dashboard Suite • Centralized Log Collection & Alerting Matrix | • Infra: Single-site vs Global Fleet aggregation • Sec: RBAC-restricted dashboard/log access | VCF Ops Dashboards & Logs
16 |  | Fleet Management | Mostly Disagree |  | • VCF Fleet Management is active, aggregating health/inventory across multiple instances • A global fleet health check is successfully executed from the VCF Management console | • Activate Fleet Management and register multiple geographic VCF instances • Validate cross-site visibility and global resource inventory consistency | • VCF Mgmt Domain • Assess & Review (VCF Ops) | • Active VCF Fleet Management Console • Signed-off Global Fleet Inventory Report | • Infra: Centralized vs Decentralized mgmt for remote sites • Sec: Mgmt traffic encryption across WAN links | VCF Fleet Management
17 |  | Capacity Management (Forecast & Right-size) | Mostly Agree |  | • Capacity modeling is providing active "Time-to-Full" projections for compute/storage • Right-sizing recommendations are being executed to reclaim idle/oversized resources | • Run capacity modeling and generate resource reclamation reports • Execute right-sizing actions and validate reclaimed capacity metrics | • Assess & Review (VCF Ops) | • Monthly Capacity & Reclamation Report • Validated Resource Forecasting Model | • Infra: Standard VM vs K8s pod autoscaling • Sec: Policy-driven vs Manual reclamation | VCF Capacity Planning
18 |  | Lifecycle Management | Strongly Disagree |  | • VCF LCM baselines (ESXi/Firmware) are defined for all workload domains • A predictive patching pre-check is successfully run to validate update readiness | • Define standardized image baselines and execute lifecycle update pre-checks • Validate non-disruptive patching workflows across multiple host clusters | • VCF Mgmt Domain • Fleet Management | • Validated Lifecycle (vLCM) Image Baseline • Documented Non-Disruptive Patching Procedure | • Infra: Vendor-specific firmware (Dell/HPE/Lenovo) • Sec: Emergency security patch workflow | VCF Lifecycle Management
19 |  | Certificate & Password Mgmt | Strongly Agree |  | • Automated certificate rotation (via SDDC Manager) is active for all components • Credential rotation policies are enforced and successfully tested in production | • Configure automated certificate rotation and implement credential rotation schedules • Execute a validated rotation test for system and service accounts | • VCF Mgmt Domain | • Signed Cert & Credential Management Plan • Successful Certificate/Password Rotation Log | • Infra: Internal vs 3rd-party CA integration • Sec: FIPS compliance for encryption keys | VCF Security & Certificates
20 |  | Compliance Management | Mostly Disagree |  | • Compliance benchmarks (PCI, HIPAA, NIST) are active for automated fleet scanning • Scheduled compliance reports are automatically delivered to audit stakeholders | • Activate platform benchmarks and configure scheduled report delivery • Validate automated audit findings against security hardening baselines | • Dashboards & Logs • Lifecycle Management | • Automated Compliance Audit Reports • Signed-off Security Hardening Baseline | • Infra: Standard vs Industry-specific mandates • Sec: Real-time vs Periodic scanning frequency | VCF Compliance & Audit
21 |  | Log Management & Analytics | Mostly Agree |  | • Centralized log collection active for all VCF components • Real-time alerting configured for critical security and system events | • Configure all VCF components to forward system logs to a centralized analysis engine • Implement real-time security alerting for critical system failures and access violations | • VCF Mgmt Domain | • Centralized Log Collection & Analysis Environment • Validated Security Event Alerting Matrix | • Infra: On-prem log storage vs Cloud-based SIEM integration • Sec: Long-term log archiving and legal hold requirements | VCF Operations for Logs
22 |  | Proactive Support & Diagnostics | Mostly Agree |  | • Support diagnostic tools (SOS) are integrated with the Unified Management Console • Automated support bundle collection and proactive heartbeats are functional | • Configure integrated support diagnostics and automated bundle collection • Validate "Skyline-style" proactive heartbeat connectivity to Broadcom | • VCF Mgmt Domain | • Functional Support & Diagnostics Dashboard • Validated Support Bundle Delivery Log | • Infra: Connected vs Disconnected support modes • Sec: Redaction requirements for support data | VCF Troubleshooting
23 |  | FinOps (Chargeback & Showback) | Mostly Agree |  | • VCF Operations is integrated with the private cloud cost-attribution model • Automated consumption reports are being delivered to business unit owners | • Integrate VCF Ops with pricing models and deliver first chargeback/showback reports • Validate cost-transparency dashboards for multi-tenant resource consumption | • Dashboards & Logs • Capacity Mgmt | • Active FinOps Cost Transparency Dashboard • Published Business Unit Showback Report | • Infra: Fixed-cost vs Pay-per-use models • Sec: Attribution of security/license overhead | VCF FinOps Management
24 |  | Hybrid Cloud Mobility (HCX) | Strongly Disagree |  | • HCX Manager and Interconnect are active and paired with a remote site • A test migration of a production-representative VM is successfully completed | • Deploy and pair HCX Manager appliances across local and remote sites • Configure Mesh services and execute a validated test migration (RAV/vMotion) | • VCF Mgmt Domain • NSX Overlay Networking • NSX Edge Connectivity | • Functional Workload Mobility Platform • Signed Migration Readiness & Test Report | • Infra: Bulk Migration vs Replication Assisted vMotion • Sec: Encryption & bandwidth throttling requirements | HCX Deployment Guide
25 | Apps & Cloud Consumption | Assess & Review (Automation/Apps) | Strongly Agree |  | • App consumption models (IaaS vs PaaS) are defined for developer teams • Service catalog taxonomy and blueprint specifications are approved | • Audit developer requirements and define blueprint standards • Map the lifecycle management path for self-service resources | • Assess & Review Workshop | • Signed App Consumption Strategy • Approved Catalog Blueprint Specs | • Infra: Standard VM vs multi-tier app stacks • Sec: Manual vs Automated approval workflows | VCF Automation Deployment
26 |  | Infrastructure-as-Code | Mostly Agree |  | • Supported source code repository is active with validated pull-request workflows • A "Hello World" infrastructure stack is successfully deployed via code | • Establish the source code repo structure and CI/CD integration • Implement secret management and validate automated provisioning | • Hybrid Cloud Mobility (HCX) • Assess & Review (Automation/Apps) | • Operational GitOps Infrastructure Repo • Validated CI/CD Provisioning Pipeline | • Infra: Terraform vs Native VCF APIs • Sec: External Secret Store integration (Vault) | GitOps & IaC Guide
27 |  | Self-Service Catalog | Mostly Disagree |  | • Service Broker portal is active with policy-driven governance enforced • Consumption metrics show active provisioning and automated lease reclamation | • Configure the portal with curated blueprints and resource quotas • Validate RBAC and test automated lease expiration/reclamation and enforced resource quotas | • VCF Mgmt Domain • Assess & Review (Automation/Apps) | • Functional Self-Service Catalog Portal • Documented Governance & Reclamation Policy and Resource Quota & Access Matrix | • Infra: Internal vs ServiceNow integration • Sec: Tenant-specific catalog visibility | Service Broker Config
28 |  | VCF Kubernetes Service (VKS) | Mostly Agree |  | • Supervisor Cluster is active with defined storage and network classes • Developer-level access to the K8s API is verified and operational | • Activate the Supervisor Cluster and define resource classes • Validate K8s endpoint connectivity and API authentication | • VCF Mgmt Domain | • Functional VKS Supervisor Cluster • Documented K8s Storage/Network Classes | • Infra: Standard vs NSX-integrated VPC networking • Sec: Public vs Private K8s API access | VKS Foundation Guide
29 |  | Enterprise Image Registry (Harbor) | Strongly Disagree |  | • Harbor registry is active with image signing and vulnerability scanning enabled • Production-ready images are successfully pushed and pulled from the registry | • Deploy Harbor and configure project-level security policies • Integrate with IdP and configure image replication or mirroring | • Self Service Catalog • VCF Kubernetes Service (VKS) | • Secure Container Registry (Harbor) Instance • Validated Registry Security & Scanning Policy | • Infra: Local vSAN vs External storage for images • Sec: Image signing (Notary) requirements | Harbor Registry Admin
30 |  | Data Services Manager (DSM) | Mostly Agree |  | • DSM provider is active with database VM templates successfully configured • Automated backup and snapshot policies are active for managed databases | • Deploy the DSM provider and define the database service catalog • Activate lifecycle management and validate automated DB provisioning | • Self Service Catalog • VCF Kubernetes Service (VKS) | • Operational DSM Management Instance • Validated Database Self-Service Workflow | • Infra: Local vSAN vs External DB storage • Sec: DB-level encryption and audit logging | Data Services Manager Guide
31 |  | Private AI Services | Strongly Agree |  | • GPU-enabled clusters are integrated with the VKS runtime for AI workloads • Fast-Suspend-Resume (FSR) is validated for maximizing GPU hardware efficiency | • Configure GPU clusters and integrate with the container runtime • Execute FSR validation tests and monitor GPU utilization metrics | None | • Functional GPU-Accelerated AI Runtime • FSR Performance & Validation Report | • Infra: vGPU vs Direct Pass-through • Sec: AI workload isolation and data sovereignty | VCF Private AI Guide
32 |  | Avi Load Balancer (App Ingress) | Mostly Agree |  | • Avi Load Balancer (NSX ALB) is active and managing L7 application ingress • Standardized SSL and WAF profiles are actively policing production endpoints | • Integrate Avi controllers and configure the native VCF ingress provider • Apply L7 security profiles and validate production traffic ingress | • VCF VPC | • Functional Avi LB Controller Cluster • Validated L7 Application Ingress Audit | • Infra: Software LB vs Hardware integration • Sec: WAF policy tuning and mTLS requirements | Avi Load Balancing Guide
33 | Resilience & Recovery | Assess & Review (DR/Cyber) | Strongly Agree |  | • Application RPO/RTO tiers are documented and signed off by the business • Cyber-recovery "Clean Room" strategy is approved by the CISO | • Audit application tiers and define recovery priority groups • Map inter-site network bandwidth to required data replication rates | • Assess & Review Workshop | • Signed BCDR & Cyber Recovery Strategy • Application Tiering & Recovery Matrix | • Active-Active vs Active-Passive • Regulatory air-gap mandates | VLR System Requirements
34 |  | Site Recovery (SRM or ACC SRM) | Mostly Agree |  | • SRM servers are paired and resource mappings (Compute/Network) are verified • Storage Policy Protection Groups (SPPG) or VM groups are successfully created | • Pair SRM instances and configure global inventory mappings • Group protected VMs and verify site-to-site resource compatibility | • VCF Mgmt Domain • NSX Overlay Networking • Assess & Review (DR/Cyber) | • Functional SRM Site Pairing Config • Documented Resource Mapping Inventory | • 1:1 Recovery vs N:1 Shared Recovery • Cross-site firewall rule sync | SRM Configuration Guide
35 |  | Cyber Recovery (Cloud or On Prem) | Strongly Disagree |  | • An isolated Cyber Recovery Vault is active with automated vulnerability scanning storing snapshots in immutable storage with retention policies enforced • A "Clean Room" recovery segment is active and isolated from the production fabric | • Establish the isolated vault and configure immutable retention locks • Configure the isolated clean room segment and execute a test restoration into the clean room and verify malware-free status | • vSAN ESA Implementation • Assess & Review (DR/Cyber) | • Functional Clean Room Environment and Operational Cyber Recovery Vault • Immutable Retention Policy and Ransomware Recovery Audit Log | • On-prem physical vs Cloud-based vault • Forensics integration requirements | Cyber Recovery Checklist
36 |  | Cloud Recovery | Mostly Agree |  | • Hybrid link to a VMC recovery endpoint is active and paired • A "Pilot Light" workload is successfully replicated and verified in the cloud | • Establish connectivity to the cloud recovery site and pair management layers • Replicate test workloads and verify cloud-side resource availability | • VCF Mgmt Domain • NSX Overlay Networking | • Operational Hybrid Cloud Recovery Link • Cloud Recovery Functional Test Report | • Cold DR vs Pilot Light (Warm) DR • Egress cost modeling for failover | VLR Cloud Recovery Onboarding
37 | Security & Compliance | Assess & Review (Security) | Strongly Agree |  | • Zero-Trust security document signed off • Tagging conventions standardized | • Audit existing security zones and define Zero-Trust tagging standards • Document policy hierarchy (Infra vs App rules) | • Assess & Review Workshop | • Signed Zero-Trust Security Design • Standardized Security Tagging Schema | • Per-tenant vs Per-app isolation • 3rd party SIEM integration | VCF Security Design
38 |  | Distributed Firewall (DFW) | Mostly Agree |  | • DFW globally active across all Workload Domains • "Default-Drop" posture enforced on non-management segments | • Enable DFW and implement "Default-Drop" on workload segments • Configure management-plane access restrictions | • NSX Overlay Networking • NSX Edge Connectivity | • Functional Global DFW Implementation • Validated "Default-Drop" Audit Log | • Greenfield vs Brownfield discovery • Dynamic Tags vs Static IP rules | NSX DFW Admin Guide
39 |  | vDefend ATP (Distributed IDS/IPS) | Mostly Disagree |  | • Advanced threat detection signatures active on production segments • IDS engine integrated with VCF Operations for real-time alerting | • Configure distributed threat signatures and integrate alerting with VCF Ops • Execute a signature update and verify real-time security alerting | • Assess & Review (Security) | • Operational IDS/IPS Protection • Active Security Alerting Dashboard | • Alert-only vs Block-and-Alert modes • Global vs Local signature mgmt | vDefend ATP Guide
40 |  | vDefend ATP (Malware Prevention & Sandbox) | Mostly Agree |  | • Malware sandboxing active for high-security tiers • System completed a validated "test fire" against a simulated threat | • Activate malware sandboxing and configure file-inspection profiles • Perform a "test fire" to verify detection and sandbox analysis | • Assess & Review (Security) | • Functional ATP Malware Protection • Malware Detection & Sandbox Report | • Local vs Cloud-based analysis • Automated vs Manual quarantine | vDefend Malware Protection
41 |  | vDefend ATP (Identity-Aware Firewall) | Strongly Disagree |  | • Security rules successfully mapping IdP user identity to firewall enforcement • User-based access logs captured and validated | • Map IdP user identity to firewall enforcement points • Validate user-based access logs within the log management system | • Identity Broker & Multi-Tenancy • Assess & Review (Security) | • Functional ID-Aware Security Policy • Signed User-Access Audit Verification | • AD vs OIDC identity sources • Remote VPN vs Internal users | NSX Identity FW Guide
42 |  | vDefend ATP (Security Intelligence) | Strongly Agree |  | • Real-time traffic visualization active to audit flows and dependencies • Security policy refined based on traffic analytics findings | • Activate traffic visualization for dependency discovery • Refine micro-segmentation policies based on automated findings | • Assess & Review (Security) | • Comprehensive App Traffic Map • Security Policy Refinement Report | • Continuous vs Periodic discovery • Automated vs Manual refinement | Security Intelligence Guide
43 |  | AVI LB (Layer-7 WAF & Ingress Security) | *Out of Scope |  | • WAF policies active for internet-facing production apps • Ingress utilizes mTLS or standardized SSL termination | • Apply WAF policies to production ingress points • Configure mTLS or SSL termination for all endpoints | • Avi Load Balancer (App Ingress) • Assess & Review (Security) | • Validated L7 WAF Protection Report • Functional mTLS/SSL Profile | • Standard OWASP vs Custom WAF • Internal vs External ingress | NSX WAF Admin Guide
44 |  | Salt (ACC) | Strongly Agree |  | • Automated enforcement of compliance and configuration standards • Dashboard provide continual status monitoring | • Deploy ACC console and Improt configuration policies • Set desired host state, remediation workflows and compliance dashboards | • Fleet Management • Compliance Management | • Minions implemented deliverying configuration management • Remediation evidence and Audit reports | • Scale of deployment, how many clusters are remediated • Various compliance/audit standards to meet | Salt Stack Configuration

## Adoption Schedule, Full
Category | Scorecard (0-6 mo) | Scorecard (6-12 mo) | Scorecard (12-18 mo) | Scorecard (18-24 mo) | Scorecard (24-36 mo) | Scorecard (36-48 mo)
Platform Foundation | +2 | +2
Storage / Datastore |  | +2
Networking & Connectivity (Network Fabric)
Operational Observability | +2 | +8
Apps & Cloud Consumption
Resilience & Recovery
Security & Compliance
Building Blocks to Complete (excluding "Assess & Review") | 4 | 12 | 5 | 5 | 5 | 5

## Example (0-6 Mths)
Block | Category | Assessment Area | Rating | Evaluation Criteria | Key Steps | Dependencies | SOW Deliverable | Variations | Reference Tech Docs
1 | Platform Foundation | Assess & Review Workshop | Strongly Agree | • VCF 9 Deployment Roadmap is signed off by executive and technical leads • Reseller Workshop mapped VCF Management Domain benefits to IT goals | • Conduct VCF 9 Capability Workshop to map business goals to VCF full-stack features • Define technical success criteria and KPIs for the 60-month adoption journey | None | • Signed VCF 9 Deployment Roadmap • Documented Business Case & KPI Map | • Infra: Greenfield vs Brownfield strategy session • Sec: Industry-specific compliance alignment (eg, HIPAA/PCI) | VCF Planning and Preparation
2 |  | Site Readiness Validation | Mostly Agree | • All VCF 9 deplpoyment prerequisites validated with a signed "Site Readiness Report" • Hardware compatibility (HCL) verified for all physical hosts and NICs | • Validate physical network (ToR, MTU) and hardware compatibility against the VCF 9 HCL • Verify DNS, NTP, and IP allocation prerequisites for the Management Domain | • Assess & Review Workshop | • Signed Site Readiness Report • Validated Infrastructure BOM/HCL Audit | • Infra: VxRail vs vSAN ReadyNode prerequisites • Sec: Air-gapped vs Connected environment prep | VCF Site Readiness Checklist
3 |  | VCF Management Domain (SDDC, Ops, NSX Manager, vCenter and Automation) | Mostly Disagree | • VCF 9 Management Domain is active, providing a single interface across all domains • Cross-component orchestration validated via global configuration task execution | • Complete the Cloud Builder workflow to deploy a healthy Management Domain (>7 appliances) • Activate the VCF Management Console and verify cross-component orchestration capabilities | • Assess & Review Workshop • Site Readiness Validation | • Functional VCF Management Console accessible via SSO • Management Domain Build & Health Report | • Infra: Standard vs Consolidated architecture deployment • HA vs non HA Management domains | VCF Installer and Domain Creation
14 | Operational Observability | Assess & Review (Operations) | Strongly Agree | • Monitoring thresholds and alerting notification paths are defined for all SDDC layers • Infrastructure metadata (Tags) is mapped to logical business applications | • Audit operational requirements for alerting and ITSM integration • Document the global tagging and metadata schema for fleet-wide visibility | • Assess & Review Workshop | • Signed Operations Design & Alerting Matrix • Documented ITSM Integration Plan | • Infra: Integrated VCF Ops vs 3rd-party (Splunk) • Sec: Data retention for performance metrics | VCF Operations Guide
17 |  | Capacity Management (Forecast & Right-size) | Mostly Agree | • Capacity modeling is providing active "Time-to-Full" projections for compute/storage • Right-sizing recommendations are being executed to reclaim idle/oversized resources | • Run capacity modeling and generate resource reclamation reports • Execute right-sizing actions and validate reclaimed capacity metrics | • Assess & Review (VCF Ops) | • Monthly Capacity & Reclamation Report • Validated Resource Forecasting Model | • Infra: Standard VM vs K8s pod autoscaling • Sec: Policy-driven vs Manual reclamation | VCF Capacity Planning

## Example (6-12 Mths)
Block | Category | Assessment Area | Capability Rating | Deliverables | Evaluation Criteria | Key Steps | Dependencies | SOW Deliverable | Variations | Reference Tech Docs
1 | Platform Foundation | Assess & Review Workshop | Strongly Agree |  | • VCF 9 Deployment Roadmap is signed off by executive and technical leads • Reseller Workshop mapped VCF Management Domain benefits to IT goals | • Conduct VCF 9 Capability Workshop to map business goals to VCF full-stack features • Define technical success criteria and KPIs for the 60-month adoption journey | None | • Signed VCF 9 Deployment Roadmap • Documented Business Case & KPI Map | • Infra: Greenfield vs Brownfield strategy session • Sec: Industry-specific compliance alignment (eg, HIPAA/PCI) | VCF Planning and Preparation
2 |  | Site Readiness Validation | Mostly Agree |  | • All VCF 9 deplpoyment prerequisites validated with a signed "Site Readiness Report" • Hardware compatibility (HCL) verified for all physical hosts and NICs | • Validate physical network (ToR, MTU) and hardware compatibility against the VCF 9 HCL • Verify DNS, NTP, and IP allocation prerequisites for the Management Domain | • Assess & Review Workshop | • Signed Site Readiness Report • Validated Infrastructure BOM/HCL Audit | • Infra: VxRail vs vSAN ReadyNode prerequisites • Sec: Air-gapped vs Connected environment prep | VCF Site Readiness Checklist
3 |  | VCF Management Domain (SDDC, Ops, NSX Manager, vCenter and Automation) | Mostly Agree |  | • VCF 9 Management Domain is active, providing a single interface across all domains • Cross-component orchestration validated via global configuration task execution | • Complete the VCF 9 installer workflow to deploy a healthy Management Domain (>7 appliances) • Activate the VCF Management Console and verify cross-component orchestration capabilities | • Assess & Review Workshop • Site Readiness Validation | • Functional VCF Management Console accessible via SSO • Management Domain Build & Health Report | • Infra: Standard vs Consolidated architecture deployment • HA vs non HA Management domains | VCF Installer and Domain Creation
4 |  | Identity Broker & Multi-Tenancy | Mostly Agree |  | • Identity Broker is active, federating VCF instances into a single SSO domain • At least one Tenant Organization is defined with isolated RBAC and resource quotas | • Deploy the VCF Identity Broker and federate with the corporate Identity Provider (IdP) • Define initial Tenant Organizations with isolated RBAC and resource quotas | • VCF Mgmt Domain | • IdP Federation Configuration Document • Functional Multi-Tenant SSO Environment | • Infra: Single-site SSO vs Global Federated SSO • Sec: SAML vs OIDC integration requirements | VCF Identity Broker Configuration
5 |  | Solution License Management | Mostly Agree |  | • All VCF 9 entitlements registered in the Business Services Portal • Licenses visible in VCF Operations, showing usage across the fleet | • Register VCF 9 entitlements are in the Business Services Portal • Activate centralized license monitoring and reporting within VCF Operations | • VCF Mgmt Domain | • License Entitlement & Allocation Map • Active Fleet-wide License Consumption Dashboard | • Infra: Connected vs Disconnected (Dark Site) licensing • Sec: Core-based vs Legacy licensing conversion | VCF Operations License Management
14 | Operational Observability | Assess & Review (VCF Operations) | Strongly Agree |  | • Monitoring thresholds and alerting notification paths are defined for all SDDC layers • Infrastructure metadata (Tags) is mapped to logical business applications. | • Audit operational requirements for alerting and ITSM integration • Document the global tagging and metadata schema for fleet-wide visibility. | • Assess & Review Workshop | • Signed Operations Design & Alerting Matrix • Documented ITSM Integration Plan. | • Infra: Integrated VCF Ops vs. 3rd-party (Splunk) • Sec: Data retention for performance metrics. | VCF Operations Guide
15 |  | Dashboards & Logs | Mostly Agree |  | • Unified dashboards provide real-time visibility from hardware to application layers • Centralized log collection is active with real-time security alerting for system failures | • Activate full-stack dashboards and configure centralized log forwarding (VCF Operations for Logs) • Create persona-based views and configure critical log-based alerts | • VCF Mgmt Domain • Assess & Review (VCF Ops) | • Functional Persona-Based Dashboard Suite • Centralized Log Collection & Alerting Matrix. | • Infra: Single-site vs. Global Fleet aggregation • Sec: RBAC-restricted dashboard/log access. | VCF Ops Dashboards & Logs
16 |  | Fleet Management | Strongly Disagree |  | • VCF Fleet Management is active, aggregating health/inventory across multiple instances • A global fleet health check is successfully executed from the VCF Management console | • Activate Fleet Management and register multiple geographic VCF instances • Validate cross-site visibility and global resource inventory consistency. | • VCF Mgmt Domain • Assess & Review (VCF Ops) | • Active VCF Fleet Management Console • Signed-off Global Fleet Inventory Report. | • Infra: Centralized vs. Decentralized mgmt for remote sites • Sec: Mgmt traffic encryption across WAN links. | VCF Fleet Management
17 |  | Capacity Management (Forecast & Right-size) | Mostly Agree |  | • Capacity modeling is providing active "Time-to-Full" projections for compute/storage • Right-sizing recommendations are being executed to reclaim idle/oversized resources. | • Run capacity modeling and generate resource reclamation reports • Execute right-sizing actions and validate reclaimed capacity metrics. | • Assess & Review (VCF Ops) | • Monthly Capacity & Reclamation Report • Validated Resource Forecasting Model. | • Infra: Standard VM vs. K8s pod autoscaling • Sec: Policy-driven vs. Manual reclamation. | VCF Capacity Planning
18 |  | Lifecycle Management | Strongly Agree |  | • VCF LCM baselines (ESXi/Firmware) are defined for all workload domains • A predictive patching pre-check is successfully run to validate update readiness. | • Define standardized image baselines and execute lifecycle update pre-checks • Validate non-disruptive patching workflows across multiple host clusters. | • VCF Mgmt Domain • Fleet Management | • Validated Lifecycle (vLCM) Image Baseline • Documented Non-Disruptive Patching Procedure. | • Infra: Vendor-specific firmware (Dell/HPE/Lenovo) • Sec: Emergency security patch workflow. | VCF Lifecycle Management
19 |  | Certificate & Password Mgmt | Strongly Agree |  | • Automated certificate rotation (via SDDC Manager) is active for all components • Credential rotation policies are enforced and successfully tested in production. | • Configure automated certificate rotation and implement credential rotation schedules • Execute a validated rotation test for system and service accounts. | • VCF Mgmt Domain | • Signed Cert & Credential Management Plan • Successful Certificate/Password Rotation Log. | • Infra: Internal vs. 3rd-party CA integration • Sec: FIPS compliance for encryption keys. | VCF Security & Certificates
20 |  | Compliance Management | Strongly Disagree |  | • Compliance benchmarks (PCI, HIPAA, NIST) are active for automated fleet scanning • Scheduled compliance reports are automatically delivered to audit stakeholders. | • Activate platform benchmarks and configure scheduled report delivery • Validate automated audit findings against security hardening baselines. | • Dashboards & Logs • Lifecycle Management | • Automated Compliance Audit Reports • Signed-off Security Hardening Baseline. | • Infra: Standard vs. Industry-specific mandates • Sec: Real-time vs. Periodic scanning frequency. | VCF Compliance & Audit
21 |  | Log Management & Analytics | Mostly Disagree |  | • Centralized log collection active for all VCF components • Real-time alerting configured for critical security and system events | • Configure all VCF components to forward system logs to a centralized analysis engine • Implement real-time security alerting for critical system failures and access violations | • VCF Mgmt Domain | • Centralized Log Collection & Analysis Environment • Validated Security Event Alerting Matrix | • Infra: On-prem log storage vs Cloud-based SIEM integration • Sec: Long-term log archiving and legal hold requirements | VCF Operations for Logs

## Lite Version
Block | Category | Assessment Area | Rating | Deliverables | Evaluation Criteria | Key Steps | Dependencies | SOW Deliverable | Variations | Reference Tech Docs
1 | Platform Foundation | Assess & Review Workshop | Strongly Agree |  | • VCF 9 Deployment Roadmap is signed off by executive and technical leads • Reseller Workshop mapped VCF Management Domain benefits to IT goals | • Conduct VCF 9 Capability Workshop to map business goals to VCF full-stack features • Define technical success criteria and KPIs for the 60-month adoption journey | None | • Signed VCF 9 Deployment Roadmap • Documented Business Case & KPI Map | • Infra: Greenfield vs Brownfield strategy session • Sec: Industry-specific compliance alignment (eg, HIPAA/PCI) | VCF Planning and Preparation
2 |  | Site Readiness Validation | Mostly Agree |  | • All VCF 9 deplpoyment prerequisites validated with a signed "Site Readiness Report" • Hardware compatibility (HCL) verified for all physical hosts and NICs | • Validate physical network (ToR, MTU) and hardware compatibility against the VCF 9 HCL • Verify DNS, NTP, and IP allocation prerequisites for the Management Domain | • Assess & Review Workshop | • Signed Site Readiness Report • Validated Infrastructure BOM/HCL Audit | • Infra: VxRail vs vSAN ReadyNode prerequisites • Sec: Air-gapped vs Connected environment prep | VCF Site Readiness Checklist
3 |  | Solution License Management | Mostly Agree |  | • All VCF 9 entitlements registered in the Business Services Portal • Licenses visible in VCF Operations, showing usage across the fleet | • Register VCF 9 entitlements are in the Business Services Portal • Activate centralized license monitoring and reporting within VCF Operations | None | • License Entitlement & Allocation Map • Active Fleet-wide License Consumption Dashboard | • Infra: Connected vs Disconnected (Dark Site) licensing • Sec: Core-based vs Legacy licensing conversion | VCF Operations License Management
4 | Datastore | Assess & Review (vSAN) | Strongly Agree |  | • Tier-1 app IOPS, latency, and throughput requirements are documented • vSAN ESA migration strategy is approved for legacy storage workloads | • Audit existing storage workloads to define SPBM performance requirements • Document the vSAN ESA failure domain and cluster-level design strategy | • Assess & Review Workshop | • Documented Storage Design & Migration Plan • Performance Baseline & Capacity Forecast | • Infra: SAN-to-vSAN migration vs Greenfield deployment • Sec: Data-at-rest encryption compliance requirements | vSAN Design Guide
5 |  | vSAN ESA Implementation | Mostly Agree |  | • vSAN ESA is active on NVMe hardware with performance testing completed • SPBM policies are defined and applied to 80% of production workloads | • Configure vSAN ESA clusters and validate hardware performance against baselines • Define and validate the SPBM policy catalog against workload requirements | • Site Readiness Validation • Assess & Review (vSAN) | • Functional vSAN ESA Cluster • Validated SPBM Policy Catalog | • Sec: Handling of mixed ESA/OSA environments • Infra: < 5ms latency (Standard) vs High-latency Stretch | vSAN Stretch Cluster Guide
6 |  | NVMe Memory Tiering | Mostly Disagree |  | • Memory tiering is active on host clusters with cold pages offloading to NVMe • Performance monitoring confirms measurable VM density increase (target 30-40%) | • Enable Memory Tiering on supported host clusters and verify NVMe targets • Validate "Cold Page" offloading and monitor for consolidation gains | • VCF Mgmt Domain | • Active NVMe Memory Tiering Configuration • Performance Report documenting consolidation gains | • Infra: Host-specific CPU/Memory architecture constraints • Sec: Data persistence requirements for tiered memory | vSphere Memory Tiering
7 | Operational Observability | Assess & Review (VCF Operations) | Strongly Agree |  | • Monitoring thresholds and alerting notification paths are defined for all SDDC layers • Infrastructure metadata (Tags) is mapped to logical business applications | • Audit operational requirements for alerting and ITSM integration • Document the global tagging and metadata schema for fleet-wide visibility | • Assess & Review Workshop | • Signed Operations Design & Alerting Matrix • Documented ITSM Integration Plan | • Infra: Integrated VCF Ops vs 3rd-party (Splunk) • Sec: Data retention for performance metrics | VCF Operations Guide
8 |  | Dashboards & Logs | Mostly Agree |  | • Unified dashboards provide real-time visibility from hardware to application layers • Centralized log collection is active with real-time security alerting for system failures | • Activate full-stack dashboards and configure centralized log forwarding (VCF Operations for Logs) • Create persona-based views and configure critical log-based alerts | • VCF Mgmt Domain • Assess & Review (VCF Ops) | • Functional Persona-Based Dashboard Suite • Centralized Log Collection & Alerting Matrix | • Infra: Single-site vs Global Fleet aggregation • Sec: RBAC-restricted dashboard/log access | VCF Ops Dashboards & Logs
9 |  | Capacity Management (Forecast & Right-size) | Mostly Agree |  | • Capacity modeling is providing active "Time-to-Full" projections for compute/storage • Right-sizing recommendations are being executed to reclaim idle/oversized resources | • Run capacity modeling and generate resource reclamation reports • Execute right-sizing actions and validate reclaimed capacity metrics | • Assess & Review (VCF Ops) | • Monthly Capacity & Reclamation Report • Validated Resource Forecasting Model | • Infra: Standard VM vs K8s pod autoscaling • Sec: Policy-driven vs Manual reclamation | VCF Capacity Planning
10 |  | Lifecycle Management | Strongly Disagree |  | • VCF LCM baselines (ESXi/Firmware) are defined for all workload domains • A predictive patching pre-check is successfully run to validate update readiness | • Define standardized image baselines and execute lifecycle update pre-checks • Validate non-disruptive patching workflows across multiple host clusters | • VCF Mgmt Domain • Fleet Management | • Validated Lifecycle (vLCM) Image Baseline • Documented Non-Disruptive Patching Procedure | • Infra: Vendor-specific firmware (Dell/HPE/Lenovo) • Sec: Emergency security patch workflow | VCF Lifecycle Management
11 |  | Compliance Management | Mostly Disagree |  | • Compliance benchmarks (PCI, HIPAA, NIST) are active for automated fleet scanning • Scheduled compliance reports are automatically delivered to audit stakeholders | • Activate platform benchmarks and configure scheduled report delivery • Validate automated audit findings against security hardening baselines | • Dashboards & Logs • Lifecycle Management | • Automated Compliance Audit Reports • Signed-off Security Hardening Baseline | • Infra: Standard vs Industry-specific mandates • Sec: Real-time vs Periodic scanning frequency | VCF Compliance & Audit
12 |  | Log Management & Analytics | Mostly Agree |  | • Centralized log collection active for all VCF components • Real-time alerting configured for critical security and system events | • Configure all VCF components to forward system logs to a centralized analysis engine • Implement real-time security alerting for critical system failures and access violations | • VCF Mgmt Domain | • Centralized Log Collection & Analysis Environment • Validated Security Event Alerting Matrix | • Infra: On-prem log storage vs Cloud-based SIEM integration • Sec: Long-term log archiving and legal hold requirements | VCF Operations for Logs
13 |  | Proactive Support & Diagnostics | Mostly Agree |  | • Support diagnostic tools (SOS) are integrated with the Unified Management Console • Automated support bundle collection and proactive heartbeats are functional | • Configure integrated support diagnostics and automated bundle collection • Validate "Skyline-style" proactive heartbeat connectivity to Broadcom | • VCF Mgmt Domain | • Functional Support & Diagnostics Dashboard • Validated Support Bundle Delivery Log | • Infra: Connected vs Disconnected support modes • Sec: Redaction requirements for support data | VCF Troubleshooting
14 |  | FinOps (Chargeback & Showback) | Mostly Agree |  | • VCF Operations is integrated with the private cloud cost-attribution model • Automated consumption reports are being delivered to business unit owners | • Integrate VCF Ops with pricing models and deliver first chargeback/showback reports • Validate cost-transparency dashboards for multi-tenant resource consumption | • Dashboards & Logs • Capacity Mgmt | • Active FinOps Cost Transparency Dashboard • Published Business Unit Showback Report | • Infra: Fixed-cost vs Pay-per-use models • Sec: Attribution of security/license overhead | VCF FinOps Management
15 | Apps & Cloud Consumption | Assess & Review (Automation/Apps) | Strongly Agree |  | • App consumption models (IaaS vs PaaS) are defined for developer teams • Service catalog taxonomy and blueprint specifications are approved | • Audit developer requirements and define blueprint standards • Map the lifecycle management path for self-service resources | • Assess & Review Workshop | • Signed App Consumption Strategy • Approved Catalog Blueprint Specs | • Infra: Standard VM vs multi-tier app stacks • Sec: Manual vs Automated approval workflows | VCF Automation Deployment
16 |  | VCF Kubernetes Service (VKS) | Mostly Agree | Out of Scope | • Supervisor Cluster is active with defined storage and network classes • Developer-level access to the K8s API is verified and operational | • Activate the Supervisor Cluster and define resource classes • Validate K8s endpoint connectivity and API authentication | • VCF Mgmt Domain | • Functional VKS Supervisor Cluster • Documented K8s Storage/Network Classes | • Infra: Standard vs NSX-integrated VPC networking • Sec: Public vs Private K8s API access | VKS Foundation Guide
17 | Resilience & Recovery | Assess & Review (DR/Cyber) | Strongly Agree |  | • Application RPO/RTO tiers are documented and signed off by the business • Cyber-recovery "Clean Room" strategy is approved by the CISO | • Audit application tiers and define recovery priority groups • Map inter-site network bandwidth to required data replication rates | • Assess & Review Workshop | • Signed BCDR & Cyber Recovery Strategy • Application Tiering & Recovery Matrix | • Active-Active vs Active-Passive • Regulatory air-gap mandates | VLR System Requirements
19 |  | Site Recovery (SRM or ACC SRM) | Mostly Agree |  | • SRM servers are paired and resource mappings (Compute/Network) are verified • Storage Policy Protection Groups (SPPG) or VM groups are successfully created | • Pair SRM instances and configure global inventory mappings • Group protected VMs and verify site-to-site resource compatibility | • VCF Mgmt Domain • NSX Overlay Networking • Assess & Review (DR/Cyber) | • Functional SRM Site Pairing Config • Documented Resource Mapping Inventory | • 1:1 Recovery vs N:1 Shared Recovery • Cross-site firewall rule sync | SRM Configuration Guide
20 |  | Cyber Recovery (Cloud or On Prem) | Strongly Disagree |  | • An isolated Cyber Recovery Vault is active with automated vulnerability scanning storing snapshots in immutable storage with retention policies enforced • A "Clean Room" recovery segment is active and isolated from the production fabric | • Establish the isolated vault and configure immutable retention locks • Configure the isolated clean room segment and execute a test restoration into the clean room and verify malware-free status | • vSAN ESA Implementation • Assess & Review (DR/Cyber) | • Functional Clean Room Environment and Operational Cyber Recovery Vault • Immutable Retention Policy and Ransomware Recovery Audit Log | • On-prem physical vs Cloud-based vault • Forensics integration requirements | Cyber Recovery Checklist
21 |  | Cloud Recovery | Mostly Agree |  | • Hybrid link to a VMC recovery endpoint is active and paired • A "Pilot Light" workload is successfully replicated and verified in the cloud | • Establish connectivity to the cloud recovery site and pair management layers • Replicate test workloads and verify cloud-side resource availability | • VCF Mgmt Domain • NSX Overlay Networking | • Operational Hybrid Cloud Recovery Link • Cloud Recovery Functional Test Report | • Cold DR vs Pilot Light (Warm) DR • Egress cost modeling for failover | VLR Cloud Recovery Onboarding
22 | Security & Compliance | Assess & Review (Security Arch) | Strongly Agree | Out of Scope | • Zero-Trust security document signed off • Tagging conventions standardized | • Audit existing security zones and define Zero-Trust tagging standards • Document policy hierarchy (Infra vs App rules) | • Assess & Review Workshop | • Signed Zero-Trust Security Design • Standardized Security Tagging Schema | • Per-tenant vs Per-app isolation • 3rd party SIEM integration | VCF Security Design
23 |  | AVI LB (Layer-7 WAF & Ingress Security) | Mostly Agree | Out of Scope | • WAF policies active for internet-facing production apps • Ingress utilizes mTLS or standardized SSL termination | • Apply WAF policies to production ingress points • Configure mTLS or SSL termination for all endpoints | • Avi Load Balancer (App Ingress) • Assess & Review (Security) | • Validated L7 WAF Protection Report • Functional mTLS/SSL Profile | • Standard OWASP vs Custom WAF • Internal vs External ingress | NSX WAF Admin Guide

## Adoption Schedule, Lite
Category | Scorecard (0-6 mo) | Scorecard (6-12 mo) | Scorecard (12-18 mo) | Scorecard (18-24 mo)
Platform Foundation | +3
Storage / Datastore
Networking & Connectivity (Network Fabric)
Operational Observability | +1
Apps & Cloud Consumption
Resilience & Recovery
Security & Compliance
Building Blocks to Complete (excluding "Assess & Review") | 4 | 5 | 5 | 5

## List
Drop Down List
Strongly Agree
Mostly Agree
Mostly Disagree
Strongly Disagree
*Out of Scope